# Cloud 2.0 Terraform Modules - Prioritized Remediation Action Plan

Document Version: 1.0
Created: 2025-11-25
Owner: Platform Engineering Team

## Priority Matrix

| Priority | Severity | Timeline | Description |
| --- | --- | --- | --- |
| P0 | Critical | Immediate (Days 1-3) | Blocks all work |
| P1 | High | Week 1 | Security risk or major blocker |
| P2 | Medium | Weeks 2-3 | Standards compliance |
| P3 | Low | Week 4+ | Nice to have |

## Phase 1: Foundation (Days 1-5)

### P0-001: Create .gitmodules Configuration

Severity: Critical
Effort: 4 hours
Owner: Platform Team Lead

Description:
The repository contains 140 submodule references but no .gitmodules file to configure their URLs.

Tasks: 1. Identify source repository URL for each module 2. Create .gitmodules file with all mappings 3. Verify format is correct 4. Commit and push

Acceptance Criteria: - [ ] .gitmodules exists with all 140 modules - [ ] Each entry has valid path and url - [ ] File passes git validation

Template:

[submodule "terraform-azurerm-aks-cluster"]
    path = terraform-azurerm-aks-cluster
    url = https://github.com/<org>/terraform-azurerm-aks-cluster.git

[submodule "terraform-azurerm-storageaccount"]
    path = terraform-azurerm-storageaccount
    url = https://github.com/<org>/terraform-azurerm-storageaccount.git

### P0-002: Initialize Submodules

Severity: Critical
Effort: 4 hours
Owner: Platform Team

Description:
After creating .gitmodules, initialize all submodules to populate module content.

Tasks: 1. Run git submodule update --init --recursive 2. Verify all 140 modules populated 3. Fix any failed submodule fetches 4. Document any modules with access issues

Commands:

git submodule update --init --recursive
git submodule status
# Verify no '-' prefixes (uninitialized) or '+' (mismatched commits)

Acceptance Criteria: - [ ] All 140 modules contain Terraform code - [ ] No submodule initialization errors - [ ] Access documented for any private repos

### P0-003: Complete Code Analysis

Severity: Critical
Effort: 8 hours
Owner: Infrastructure Team

Description:
Re-run the audit with populated module content to identify actual issues.

Tasks: 1. Parse all .tf files in each module 2. Extract variables, outputs, resources 3. Identify hard-coded values 4. Detect security issues 5. Update workspace-analysis.json

Acceptance Criteria: - [ ] workspace-analysis.json updated with real data - [ ] All modules catalogued - [ ] Issues documented with line numbers

## Phase 2: Security Audit (Week 1)

### P1-001: Security Vulnerability Scan

Severity: High
Effort: 16 hours
Owner: Security Team

Description:
Run security scanners against all module code.

Tasks: 1. Install and configure tfsec 2. Install and configure checkov 3. Run against all modules 4. Categorize findings by severity 5. Document remediation requirements

Commands:

# Run tfsec on all modules
find . -name "*.tf" -exec dirname {} \; | sort -u | while read dir; do
    echo "Scanning: $dir"
    tfsec "$dir" --format json > "results/${dir//\//_}.json"
done

# Run checkov
checkov -d . --output-file-path results/

Acceptance Criteria: - [ ] All modules scanned - [ ] No Critical findings remain - [ ] High findings documented with remediation plans

### P1-002: Hard-Coded Secrets Detection

Severity: High
Effort: 8 hours
Owner: Security Team

Description:
Identify any hard-coded secrets, API keys, or credentials in module code.

Tasks: 1. Run git-secrets or similar tool 2. Search for common secret patterns 3. Check for subscription IDs, tenant IDs 4. Verify no API keys in code

Patterns to Search:

# Azure patterns
grep -rn "subscription_id\s*=" . --include="*.tf"
grep -rn "tenant_id\s*=" . --include="*.tf"
grep -rn "client_secret\s*=" . --include="*.tf"

# Generic secret patterns
grep -rn "password\s*=" . --include="*.tf"
grep -rn "api_key\s*=" . --include="*.tf"
grep -rn "secret\s*=" . --include="*.tf"

Acceptance Criteria: - [ ] No hard-coded secrets found - [ ] All secrets use variables or Key Vault - [ ] Sensitive variables marked sensitive = true

### P1-003: IAM Policy Review

Severity: High
Effort: 8 hours
Owner: Security Team

Description:
Review all role assignments and IAM policies for least privilege.

Tasks: 1. Identify all role assignment resources 2. Review scope of assignments 3. Check for wildcard permissions 4. Document overly permissive roles

Acceptance Criteria: - [ ] No wildcard (*) principals - [ ] Roles scoped appropriately - [ ] Built-in roles preferred over custom

## Phase 3: Standardization (Weeks 2-3)

### P2-001: Create Module Template

Severity: Medium
Effort: 8 hours
Owner: Platform Team

Description:
Create and document canonical module template for all modules to follow.

Tasks: 1. Create template repository structure 2. Document required files 3. Create variable and output standards 4. Add testing skeleton

Deliverables: - module-template/ directory (see template in this audit) - Documentation in SOP.md

Acceptance Criteria: - [ ] Template created and tested - [ ] Documentation complete - [ ] Example usage works

### P2-002: Provider Version Pinning

Severity: Medium
Effort: 8 hours
Owner: Infrastructure Team

Description:
Ensure all modules pin provider versions consistently.

Tasks: 1. Audit current provider constraints 2. Define standard versions 3. Update all modules 4. Test compatibility

Standard Versions:

terraform {
  required_version = ">= 1.4"
  required_providers {
    azurerm = {
      source  = "hashicorp/azurerm"
      version = "~> 3.80"
    }
  }
}

Acceptance Criteria: - [ ] All modules have versions.tf - [ ] All use same provider version constraint - [ ] terraform validate passes

### P2-003: Variable Standardization

Severity: Medium
Effort: 16 hours
Owner: Module Owner

Description:
Standardize variable names across all modules.

Tasks: 1. Audit current variable names 2. Map to canonical names 3. Add backward-compatible aliases 4. Update documentation

Canonical Names: | Current Variations | Canonical | |——————-|———–| | env, environ, environment_name | environment | | proj, project_name, app | project | | loc, region, azure_region | location | | tags, resource_tags | tags |

Migration Pattern:

# Old variable (deprecated)
variable "env" {
  description = "DEPRECATED: Use 'environment' instead"
  type        = string
  default     = null
}

# New canonical variable
variable "environment" {
  description = "Environment name (dev, staging, prod)"
  type        = string
}

# Backward-compatible local
locals {
  environment = coalesce(var.environment, var.env, "dev")
}

Acceptance Criteria: - [ ] All modules use canonical names - [ ] Old names deprecated but functional - [ ] 90-day deprecation timeline set

### P2-004: Add Missing Documentation

Severity: Medium
Effort: 24 hours
Owner: Module Owner

Description:
Create or update README.md for all modules.

Tasks: 1. Identify modules missing README 2. Generate README from terraform-docs 3. Add usage examples 4. Document inputs/outputs

Command:

for module in terraform-*; do
    terraform-docs markdown table "$module" > "$module/README.md"
done

Acceptance Criteria: - [ ] All modules have README.md - [ ] All variables documented - [ ] All outputs documented - [ ] Usage example provided

### P2-005: Consolidate Environment Modules

Severity: Medium
Effort: 40 hours
Owner: Infrastructure Team

Description:
Merge environment-specific modules into single parameterized modules.

Affected Modules: - terraform-azurerm-infrastructure-iaas-dev - terraform-azurerm-infrastructure-iaas-qa - terraform-azurerm-infrastructure-iaas-uat - terraform-azurerm-infrastructure-iaas-stg - terraform-azurerm-infrastructure-iaas-prod - terraform-azurerm-infrastructure-iaas-dr - terraform-azurerm-infrastructure-iaas-trng

Tasks: 1. Analyze differences between modules 2. Create single parameterized module 3. Add environment variable 4. Create tfvars for each environment 5. Test all environments 6. Deprecate old modules

Acceptance Criteria: - [ ] Single module supports all environments - [ ] Old modules deprecated - [ ] Consumer migration guide provided

## Phase 4: Quality & CI/CD (Week 4)

### P3-001: Add Testing

Severity: Low
Effort: 24 hours
Owner: Infrastructure Team

Description:
Add automated tests to high-priority modules.

Tasks: 1. Set up Terratest framework 2. Create tests for key modules 3. Add to CI/CD pipeline 4. Document test procedures

Priority Modules for Testing: 1. terraform-azurerm-aks-cluster 2. terraform-azurerm-virtual-network 3. terraform-azurerm-storageaccount 4. terraform-azurerm-azure-key-vault

Acceptance Criteria: - [ ] Terratest framework configured - [ ] Top 10 modules have tests - [ ] Tests run in CI/CD

### P3-002: Implement Module Registry

Severity: Low
Effort: 24 hours
Owner: Platform Team

Description:
Set up private module registry for better version management.

Options: 1. Terraform Cloud Private Registry 2. Azure DevOps Artifact Feed 3. Self-hosted (e.g., Artifactory)

Tasks: 1. Choose registry solution 2. Configure authentication 3. Publish initial modules 4. Update consumer documentation

Acceptance Criteria: - [ ] Registry deployed - [ ] Top modules published - [ ] Consumers can reference via registry

### P3-003: CI/CD Pipeline

Severity: Low
Effort: 16 hours
Owner: Platform Team

Description:
Create CI/CD pipeline for module validation.

Pipeline Stages: 1. Lint (tflint) 2. Format (terraform fmt) 3. Validate (terraform validate) 4. Security (tfsec, checkov) 5. Test (terratest) - on merge 6. Publish - on tag

Acceptance Criteria: - [ ] Pipeline configured - [ ] All stages working - [ ] Automatic on PR

## Summary Timeline

Week 1
├── Days 1-3: Create .gitmodules, initialize submodules
├── Days 3-5: Complete code analysis
└── Days 3-5: Begin security scan

Week 2
├── Complete security scan
├── Remediate critical/high findings
├── Create module template
└── Begin provider standardization

Week 3
├── Complete provider standardization
├── Variable standardization (begin)
├── Add documentation
└── Begin environment module consolidation

Week 4
├── Complete environment consolidation
├── Add testing to key modules
├── Set up module registry
└── Configure CI/CD pipeline

## Resource Requirements

| Role | FTE Weeks | Responsibilities |
| --- | --- | --- |
| Platform Team Lead | 2 | Coordination, .gitmodules |
| Security Engineer | 1.5 | Scans, remediation |
| Infrastructure Engineer | 3 | Analysis, standardization |
| Module Owner(s) | 2 | Documentation, fixes |

Total Estimated Effort: 8.5 FTE weeks (~340 hours)

## Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Submodule repos inaccessible | High | Document URLs, request access early |
| Breaking changes during consolidation | High | Maintain backward compatibility |
| Consumer disruption | Medium | Communicate deprecation timeline |
| Resource constraints | Medium | Prioritize P0/P1 items |

## Success Metrics

| Metric | Current | Target | Timeline |
| --- | --- | --- | --- |
| Modules with code | 0 | 140 | Week 1 |
| Critical issues | Unknown | 0 | Week 2 |
| High issues | Unknown | 0 | Week 3 |
| Modules with README | Unknown | 140 | Week 3 |
| Modules with tests | Unknown | 20+ | Week 4 |
| Environment modules | 8 | 1 | Week 4 |

## Approval

| Role | Name | Date | Signature |
| --- | --- | --- | --- |
| Platform Lead |  |  |  |
| Security Lead |  |  |  |
| Infrastructure Lead |  |  |  |